## Sheet1
Scheme | Contractor | Type of Contract | Type of Work | Floor Area | Contract Price | Final Account | Contract Date | Completion Date | Actual Completion Date
HE Schemes | H&J Martin | D&B | Refurbishment | 772 m2 | 755 k | 737 k | 2010-02-01 | 2010-04-01 | 2010-04-01
DDA Schemes | Pattons | D&B | Refurbishment - various works resulting from Dda audits, ramps, accessible WC's, access etc. | n/a | 403 k | 413 k | 2010-01-01 | 2010-03-01 | 2010-09-01
Nubia Youth Club | H&J Martin | D&B | Refurbishment works | 550 m2 | 321 k | 316 k | 2010-02-01 | 2010-04-01 | 2013-03-01
Stranmillis | Farrans | D&B | Construction of new playground area and extension to provide staffroom | n/a | 467 k | TBA | 2012-09-01 | 2013-03-01 | 2013-03-01
Mitchell House | Farrans | D&B | New Science Mobile and WC refurbishment | 250 m2 | 333 k | TBA | 2013-01-01 | 2013-04-01 | 2013-04-01
Youth Club Pitches | Pattons | D&B | Refurbishment of existing surfaces | 2787 m2 | 337 k | 365 k | 2012-01-01 | 2012-03-01 | 2012-06-01
Ashfield Boys | Farrans | D&B | Refurbishment works | 993 m2 | 444 k | TBA | 2013-07-01 | 2013-09-01 | 2013-09-01
Taughmonagh | Farrans | D&B | New Build Primary and Nursery School | 2216 m2 | 3,253 k | 3380 k | 2011-01-01 | 2012-06-01 | 2012-06-01
Ravenscroft Nursery | H&J Martin | D&B | New Build Nursery School | 288 m2 | 585 k | 607 k | 2009-02-01 | 2009-08-01 | 2009-08-01
Glendhu Nursery | H&J Martin | D&B | New Build Nursery School | 172 m2 | 425 k | 434 k | 2009-02-01 | 2009-08-01 | 2009-08-01
Grosvenor Grammar | Pattons | PFI | New Build post primary school | 13,856 m2 | 19,456 k | 21,154 k | 2008-03-01 | 2010-07-01 | 2010-07-01
Orangefield Primary School and Nursery School | Pattons | PFI | New Build Primary and Nursery School | 2,745 m2 | 4,929 k | 5,361 k | 2008-03-01 | 2009-05-01 | 2009-05-01
Ashfield Girls | H&J Martin | PFI | New Build post primary school | 10,011 m2 | 16,176 k | 17671 k | 2008-03-01 | 2009-09-01 | 2009-09-01
Boys Model | Farrans | PFI | New Build post primary school | 14,989 m2 | 24,624 k | 26,365 k | 2008-03-01 | 2011-01-01 | 2011-01-01
Girls Model | Farrans | PFI | New Build post primary school | 14,919 m2 | 21,741 k | 23,372 k | 2008-03-01 | 2010-05-01 | 2010-05-01