## Sheet1
Streatham Common Playground Budget
Budget Breakdown
Overall Budget |  | 817454.63
Works Budget |  | 700000
Contract Sum |  |  |  | 634807.04
External Cosultants Fees |  |  |  | 62310
Establishment Costs |  |  |  | 57629
|  | Forecasted spend |  | 754746.04
Summary | Starting Budget |  | 817454.63
| Forecasted Spend |  | -754746.04
| Contingencies |  | 62708.59
Construction Costs
| Gross Valuation | Retention | Less Previous Payment | Actual Payments
Valuation No. 1 | 50995 | 2549.75 | 0 |  | 48445.25
Valuation No. 2 | 166847.96 | 8342.4 | 48445.25 |  | 110060.31
Valuation No. 3 | 466611 | 23330.55 | 158505.56 |  | 284774.89
Valuation No. 4 | 593682.8 | 14842.07 | 443280.45 |  | 135560.29
Valuation No. 5 | 0
|  | Payments to date |  |  | 578840.74
Draft Final account is currently being assessed.
2.5% retentoin of final Contract sum retained for 12 months.