## Sheet1
Warwickshire County Council - Freedom of Information request: 3173928.
Please provide details, including outcomes, of all fire safety compliance inspections conducted on high-rise residential buildings since 14 June 2017.
Building name | Address | Date of Inspection | Outcome | Time frames for work completion, re-inspection date and notes.
Ashwood Court | Rounds Gardens, Rugby, CV21 2UQ | 2017-06-21 | Non-compliant | Schedule of works issued, re-inspection date = 10/01/2018. Extension of time granted on 10/01/2018 until 18/04/2018.
Beechwood Court | Rounds Gardens, Rugby, CV21 2UQ | 2017-06-21 | Non-compliant | Schedule of works issued, re-inspection date = 10/01/2018. Extension of time granted on 10/01/2018 until 18/04/2018
Royal Court | Rounds Gardens, Rugby, CV21 2UQ | 2017-06-21 | Non-compliant | Schedule of works issued, re-inspection date = 10/01/2018. Extension of time granted on 10/01/2018 until 18/04/2018.
Fairway Court | Biart Place Flats, Clifton Road, Rugby, CV21 3QT | 2017-06-22 | Non-compliant | Schedule of works issued, re-inspection date = 10/01/2018. Extension of time granted on 10/01/2018 until 18/04/2018
Green Court | Biart Place Flats, Clifton Road, Rugby, CV21 3QT | 2017-06-22 | Non-compliant | Schedule of works issued, re-inspection date = 10/01/2018. Extension of time granted on 10/01/2018 until 18/04/2018.
Ashton Court | 2 - 92 Ashton Court, The Crest, Newland Road, Leamington Spa, CV32 7PX | 2017-06-22 | Non-compliant | Schedule of works issued, re-inspection date = 20/09/2017. Extension of time granted on 19/09/2017 until 13/12/2017. Still ongoing.
Christine Ledger Court | 14 - 67 Christine Ledger Square | 2017-06-22 | Non-compliant | Schedule of works issued, re-inspection date = 20/09/2017. Extension of time granted on 19/09/2017 until 13/12/2017. Stilll ongoing.
Eden Court | Masno Avenue, Leamington Spa, CV32 7PG | 2017-06-22 | Non-compliant | Schedule of works issued, re-insoection date = 20/09/2017. Extension of time granted on 19/09/2017 until 13/12/2017. Still ongoing.
Radcliffe Gardens | 1 - 54 Radcliffe Gardens, Brunswick Street, Leamington Spa, CV31 2DY | 2017-06-22 | Non-compliant | Schedule of works issued, re-inspection date = 20/09/2017. Extension of time granted on 19/09/2017 until 13/12/2017. Still ongoing.
Southorn Court | 1 - 92 Southorn Court, The Crest, Newland Road, Leamington Spa, CV32 7PU | 2017-06-22 | Non-compliant | Schedule of works issued, re-inspection date = 20/09/2017. Extension of time granted on 19/09/2017 until 13/12/2017. Still ongoing.
Stamford Gardens | 29 - 79 Stamford Gardens, Rugby Road, Leamington Spa, CV32 6DP | 2017-06-22 | Non-compliant | Schedule of works issued, re-inspection date = 20/09/2017. Extension of time granted on 19/09/2017 until 13/12/2017. Still ongoing.
Westbrook House | 1 - 64 Westbrook House, New Brook Street, Leamington Spa, CV32 5AS | 2017-06-22 | Non-compliant | Schedule of works issued, re-inspection date = 20/09/2017. Extension of time granted on 19/09/2017 until 13/12/2017. Still ongoing.
Holiday Inn | 212 Abbey End, Smalley Place, Kenilworth, CV8 1ED | 2017-06-26 | Compliant | Schedule of works issued, no re-inspection date (will fall into Risk Based Inspection Program - RBIP).
Manor Court | Avenue Road, Leamington Spa, CV31 3NL | 2017-06-28 | Non-compliant | Schedule of works issued, re-inspection date = 27/09/2017. Extension of time granted on 29/09/2017 until 20/12/2017. Still ongoing.
The Space | Clarendon Avenue, Leamington Spa, CV32 5PJ | 2017-06-29 | Non-compliant | Schedule of works issued, re-inspection date = 27/09/2017. Extension of time granted on 29/09/2017 until 20/12/2017. Still ongoing.
44 Clarendon Square | Leamington Spa, CV32 5QZ | 2017-06-29 | Non-compliant | Schedule of works issued, re-inspection date = 27/09/2017. Extension of time granted on 19/09/2017 until 13/12/2017. Still ongoing.
44 - 62 Binswood Street | Leamington Spa, CV32 5QZ | 2017-06-29 | Non-compliant | Schedule of works issued, re-inspection date = 27/09/2017. Extension of time granted on 19/09/2017 until 13/12/2017. Still ongoing.
Bridge House | Sir Anthony Eden Way, Warwick, CV34 5FR | 2017-06-29 | Compliant | Schedule of works issued, no re-inspection date (will fall into RBIP).
Premier Inn | Opus 40 Business Park, Haywood Road, Warwick, CV34 5AH | 2017-06-30 | Non-compliant | Schedule of works issued, no re-inspection date (will fall into RBIP).
Regency House | Newbold Terrace, Leamington Spa, CV32 4HD | 2017-06-30 | Non-compliant | Schedule of works issued, re-inspection date = 27/09/2017. Extension of time granted on 29/09/2017 until 20/12/2017. Still ongoing.
9 Clarendon Place | 9 Clarendon Place, Leamington Spa, CV32 5QL | 2017-07-04 | Non-compliant | Schedule of works issued, no re-inspection date (will fall into RBIP).
Clarence Mansions (1 -6, 8 - 17, 22 - 31) | Clarence Terrace, Clarence Terrace, Leamington Spa, CV32 5LD | 2017-09-11 | Non-compliant | Schedule of works issued, re-inspection date = 04/12/2017. Still ongoing.
George House | The Parade, Leamington Spa | 2017-09-27 | Non-compliant | Schedule of works issued, re-inspection date = 20/12/2017. Still ongoing.
William House | The Parade, Leamington Spa | 2017-09-28 | Non-compliant | Schedule of works issued, re-inspection date = 20/12/2017. Still ongoing.
Villiers House | Clarendon Avenue, Leamington Spa, CV32 5PJ | 2018-03-27 | Non-compliant | Schedule of works issued, re-inspection date = 26/06/2018. Still ongoing.